## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Bingo online shop
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 14.1.2024 | Inas Bajrektarević | 1. Open Google Chrome web browser 2. Go to www.onlineshop.ba 3. Click on category "Dječiji svijet" 4. Click on "Igračka Građevinski sto" and then "Dodaj u Korpu" 5. Change "Količina" to three 6. Continue with the order and you will notice that the price of the product does not increase when you change the quantity to three |  | Post-Deployment | High | Developer | 14.1.2024 | 2h | New | Price increase |  |  | bad code | New
2 | 15.1.2024 | Inas Bajrektarević | 1. Open Google Chrome web browser 2. Go to www.onlineshop.ba 3. Click on "Kategorije" 4. Click on category "Električni alat" 5. Do a filter by price by putting the price 600-1000 6. It will show the filtered products, but the price range that we specified returns to the default state |  | Post-Deployment | Low | Developer | 15.1.2024 | 2h | New | Selected price range |  |  | process | In Progress | Medium | Initiating | Concept
3 | 16.1.2024 | Inas Bajrektarević | 1. Open Google Chrome web browser 2. Go to www.onlineshop.ba 3.Click on category "Namještaj". 4.Do a filter "Sortiraj po cijeni (najniža-najviša)" 5. Then do a filter by price by putting the price 100-300.It does not sort at all,only reload the page |  | Post-Deployment | High | Developer | 16.1.2024 | 1h | New | Sort items |  |  | Bad code | Completed | Low | Planning | Requirements
4 | 16.1.2024 | Inas Bajrektarević | 1. Open Google Chrome web browser 2. Go to www.onlineshop.ba 3. Write your mail in text box on bottom page and click button "Prijavite se". 4. We should get some feedback about this action, but we didn't get any notification |  | Post-Deployment | Medium | Developer | 16.1.2024 | 1h | New | Success message |  |  | commnication |  |  | Executing/Controlling | Design
5 | 16.1.2024 | Lamija Babović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Choose a category (Kategorija: Asesoari). 4. Pick an item from list of products (Naušnice). 5. Click "Dodaj u korpu" button. 6. Cart page is loaded with item in the list. Expected result: Message that confirm an item was added to cart. |  | Post-Deployment | Medium | Developer | 16.1.2024 | 1 h | New | Success message |  |  | Bad code |  |  | Closing | Development
6 | 16.1.2024 | Lamija Babović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba 3. Choose a category (Kategorija: Asesoari). 4. Pick an item from list of products (Naušnice). 5. Click "Dodaj u korpu" button. 6. Cart page is loaded with item in the list. 7. Click logo to redirect on home page. 8. Choose a category (Kategorija: Asesoari) 9. Pick same item that is already added to cart (Naušnice) 10. Click "Dodaj u korpu" button 11. Cart page is loaded. There are two same items in the list. Expected result: Quantity of the item increased. |  | Post-Deployment | High | Developer | 16.1.2024 | 4 h | New | Prevent duplicating items, increase quantity |  |  | Bad code |  |  |  | Testing
7 | 16.1.2024 | Lamija Babović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba 3. Choose an item from home page that has "Kupi odmah" button. 4. Go to "Recenzije" tab. 5. Select star to rate the item and leave a space in message box. 6. Feedback is sent. Expected result: Error message because there is no message. |  | Post-Deployment | Medium | Developer | 16.1.2024 | 2h | New | Error message |  |  | Bad code |  |  |  | Documentation and Training
8 | 17.1.2024 | Ismihana Međedović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba 3. Click on button "Prijava" 4. Enter correct email and password information for the already created account 5. Click button "Login" 6. In the upper right corner is the name of the user Expected result: message "Dobro došli ImeKorinika " |  | Post-Deployment | Low | Developer | 18.1.2024 | 30 min | New | Success message |  |  | Bad code |  |  |  | Deployment
9 | 17.1.2024 | Ismihana Međedović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Choose a category (Kategorija: Asesoari). 4. Pick an item from list of products (Naušnice). 5. Click "Dodaj u korpu" button. 6. Cart page is loaded with item in the list. 7. Click the "X" button to delete the product from the cart. Expected result: Message that confirm the item has been deleted from the cart. |  | Post-Deployment | Medium | Developer | 17.1.2024 | 1h | New | Success message |  |  | Bad code |  |  |  | Post-Deployment
10 | 17.1.2024 | Ismihana Međedović | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Click on filter for search name of products 4. Enter a space in the field 5. Then click button for search (button with the magnifying glass icon) 6.We have received a list of some products Expected result: Error message because there is no name of product. |  | Post-Deployment | Medium | Developer | 17.1.2024 | 2h | New | Error message |  |  | Bad code
11 | 18.1.2024 | Mustafa Isić | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Click on "Kalei bebi oprema" 4. Click on "Kategorije." dropdown menu. 5. None of the items are loeaded. Expected result: All the items from the "Kategorije" dropdown should be shown |  | Post-Deployment | Medium | Developer | 18.1.2024 | 1h | New | Items shown |  |  | Bad code
12 | 18.1.2024 | Mustafa Isić | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Choose a category (Kategorija: Mobiteli). 4.Inserting text "iPhone" into filter for minimum price range 5. Click on button "Filter". 6. The filter is accepted and the products are shown. Expected result: An error message that says "Nema artikala za prikaz" because you can't enter text into a price filter range |  | Post-Deployment | Medium | Developer | 18.1.2024 | 2h | New | Error message |  |  | bad code
13 | 18.1.2024 | Mustafa Isić | 1. Open Chrome web browser. 2. Go to https://onlineshop.ba. 3. Choose a category (Kategorija: Mobiteli). 4. The page is loaded and on the dropdown that shows the categories has an extra item. Expected result: The categories should be loaded without the extra code |  | Post-Deployment | Low | Developer | 18.1.2024 | 10 min | New | Remove extra code |  |  | bad code
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).